## SPRINT 1.0
TEAM URSULA - Sprint 1
Scrum Master: Sarah Price
Story
Steps | Explanation | Layer | CRUD | Data Type | Software Used | Points | Owner | Date To Be Completed | Status
1 | User will store data; Date, Latitude, Longitude, Depth, Magnitude, Magnitude Type, Place, Province | Database Layer | CREATE | Location Markers | SQL | 10
Database DDL, DML
2 | User will get all Earthquakes | Database Layer | READ | Location Markers | SQL | 3
sp_GetAllEarthquakes, sp_GetEarthquakeByID
3 | User will update Earthquake by Date, Location or ID | Database Layer | UPDATE | Location Markers | SQL | 10
sp_ UpdateEarthquakeByID
4 | User will delete Earthquake by ID | Database Layer | DELETE | Location Markers | SQL | 2
sp_DeleteEarthquakebyID
5 | Create location object - Takes the data from SQL to create a location marker | Business Logic Layer | CREATE | Location Markers | Visual Studios | 10
User can select a year which will grab the location markers for that time period
6 | Coresponds with create - File reader will retrieve data stored in SQL | Business Logic Layer | READ | Location Markers | Visual Studios | 3
C# will corepsond with SQL
7 | User will be able to update the Earthquake by ID | Business Logic Layer | UPDATE | Location Markers | Visual Studios | 10
Private and public functions will be used so data can not be manipulated - tests in place
8 | User can delete their selection of Earthquakes - program will loop so they can add a new selection | Business Logic Layer | DELETE | Location Markers | Visual Studios | 2
C# code so the user can click delete or clear
9 | User can create markers by selecting a desired year | Presentation Layer | CREATE | Location Markers | ASPX, HTML | 10
Location markers will be placed on google map
10 | User can click specific location marker to retrieve data on specific Earthquakes | Presentation Layer | READ | Location Markers | ASPX, HTML | 3
All information on that earthquake will be displayed to the screen
11 | User can delete selection/clear selection | Presentation Layer | DELETE | Location Markers | ASPX, HTML | 10
Delete button/ Clear selection button
12 | User can update selection | Presentation Layer | UPDATE | Location Markers | ASPX, HTML | 2
Update selection button
Summary | [5 empty] | 75
In sprint one we will create a database for the Earthquake data in Microsoft SQL Server. Stored procedures will be created in this software along side the DDL and DML. In visual studios we will implement code from the Airport assignment which will read and create Earthquake locations. In the presentation layer the user will be able to select a year to see all Earthquake location markers from that time frame on a google map. They will be able to select different location markers and the distance between the earthquakes and the corresponding data will appear. The user can select between one to two locations to see the data on each earthquake. The database layer, business logic layer and presentation layer will all communicate with each other and will all be CRUD complete.

## SPRINT 2.0
TEAM URSULA - Sprint 2
Scrum Master: Bibhu
Story
Steps | Explanation | Layer | CRUD | Data Type | Software Used | Points | Owner | Date To Be Completed | Status
1 | User will store data; Date, Latitude, Longitude, Depth, Magnitude, Magnitude Type, Place, Province | Database Layer | CREATE | Polylines | SQL | 15
Database DDL, DML
2 | User will get all Earthquakes | Database Layer | READ | Polylines | SQL | 3
sp_GetAllEarthquakes, sp_GetEarthquakeByID
3 | User will update Earthquake by Date, Location or ID | Database Layer | UPDATE | Polylines | SQL | 15
sp_ UpdateEarthquakeByID
4 | User will delete Earthquake by ID | Database Layer | DELETE | Polylines | SQL | 2
sp_DeleteEarthquakebyID
5 | Create location object - Takes the data from SQL to create a location marker and polyline | Business Logic Layer | CREATE | Polylines | Visual Studios | 15
C# code will create a polyline object between selected earthquakes within the desired year
6 | Coresponds with create - File reader will retrieve data stored in SQL | Business Logic Layer | READ | Polylines | Visual Studios | 3
C# will corepsond with SQL - it wil now read the distance to create the polyline if option is selected
7 | User will be able to update the Earthquake by ID | Business Logic Layer | UPDATE | Polylines | Visual Studios | 15
Private and public functions will be used so data can not be manipulated - tests in place. Earthquakes selected can be updated to create a polyline between new selection
8 | User can delete their selection of location markers or polyline selection | Business Logic Layer | DELETE | Polylines | Visual Studios | 2
C# code so the user can click delete or clear. User can delete just the polyline selection or clear all data.
9 | User can create markers by selecting a desired year - and can now select a polyline option | Presentation Layer | CREATE | Polylines | ASPX, HTML | 15
Location markers will be placed on google map and polylines between selected earthquakes.
10 | User can click specific location marker to retrieve data on specific Earthquakes - with or without the polyline | Presentation Layer | READ | Polylines | ASPX, HTML | 3
All information on that earthquake will be displayed to the screen. The interface will read and create the polyline.
11 | User can delete selection/clear selection - just the polyline or all data | Presentation Layer | DELETE | Polylines | ASPX, HTML | 15
Delete button/ Clear selection button
12 | User can update selection to create a new polyline | Presentation Layer | UPDATE | Polylines | ASPX, HTML | 2
Update selection button
Summary | [5 empty] | 105
In sprint two we will be updating our code from sprint one to now create polylines between earthquakes. The polylines will appear only if the user selects the option on the side. All data from each earthquake will still appear on the side. There will be a button selection where the user can click "show polyline." There will be a clear, delete, and update selection implemented for the polylines as well.

## SPRINT 3.0
TEAM URSULA - Sprint 3
Scrum Master: Biswash
Story
Steps | Explanation | Layer | CRUD | Data Type | Software Used | Points | Owner | Date To Be Completed | Status
1 | User will store data; Date, Latitude, Longitude, Depth, Magnitude, Magnitude Type, Place, Province | Database Layer | CREATE | Polygons | SQL | 20
Database DDL, DML
2 | User will get all Earthquakes | Database Layer | READ | Polygons | SQL | 3
sp_GetAllEarthquakes, sp_GetEarthquakeByID
3 | User will update Earthquake by Date, Location or ID | Database Layer | UPDATE | Polygons | SQL | 20
sp_ UpdateEarthquakeByID
4 | User will delete Earthquake by ID | Database Layer | DELETE | Polygons | SQL | 2
sp_DeleteEarthquakebyID
5 | Create location object - Takes the data from SQL to create a location marker and polygon | Business Logic Layer | CREATE | Polygons | Visual Studios | 20
A polygon object will be created within a specific distance of selected earthquakes
6 | Coresponds with create - File reader will retrieve data stored in SQL | Business Logic Layer | READ | Polygons | Visual Studios | 3
C# will corepsond with SQL to read and create the polyogn shape
7 | User will be able to update the Earthquake by ID/ Update selection | Business Logic Layer | UPDATE | Polygons | Visual Studios | 20
Private and public functions will be used so data can not be manipulated - tests in place. Earthquakes selected can be updated to create a polygon between new selection
8 | User can delete their selection of location markers, polyline selection and now polygon selection | Business Logic Layer | DELETE | Polygons | Visual Studios | 2
C# code so the user can click delete or clear. User can delete just the polyline selection or clear all data.
9 | User can create markers by selecting a desired year - and can now select a polygon option | Presentation Layer | CREATE | Polygons | ASPX, HTML | 20
Location markers will be placed on google map and polygons will be placed around selected earthquakes.
10 | User can click specific location marker to retrieve data on specific Earthquakes | Presentation Layer | READ | Polygons | ASPX, HTML | 3
All information on that earthquake will be displayed to the screen. This will now include the distance information of the polygons.
11 | User can delete selection/clear selection - just the polygon or all data | Presentation Layer | DELETE | Polygons | ASPX, HTML | 20
Delete button/ Clear selection button
12 | User can update selection to create new polygons | Presentation Layer | UPDATE | Polygons | ASPX, HTML | 2
Update selection button
Summary | [5 empty] | 135
In sprint three we will further update our project to now create circular polygons within a specific distance around the earthquake of the users choice. This will help the user to visualize what surrounding areas would be most affected by the earthquakes. Just like the polyline option, there will be a delete, clear and update selection for the polygons. User can now pick polylines, polygons or both.

## SPRINT 4.0
TEAM URSULA - Sprint 4
Scrum Master: Sarah Duplan
Story
Steps | Explanation | Layer | CRUD | Data Type | Software Used | Points | Owner | Date To Be Completed | Status
1 | User will store data; Date, Latitude, Longitude, Depth, Magnitude, Magnitude Type, Place, Province | Database Layer | CREATE | Heatmap | SQL | 10
Database DDL, DML
2 | User will get all Earthquakes | Database Layer | READ | Heatmap | SQL | 2
sp_GetAllEarthquakes, sp_GetEarthquakeByID
3 | User will update Earthquake by Date, Location or ID | Database Layer | UPDATE | Heatmap | SQL | 10
sp_ UpdateEarthquakeByID
4 | User will delete Earthquake by ID | Database Layer | DELETE | Heatmap | SQL | 2
sp_DeleteEarthquakebyID
5 | Create location object - Takes the data from SQL to create a location marker and heatmap | Business Logic Layer | CREATE | Heatmap | Visual Studios | 10
User can select a year which will grab the location markers for that time period
6 | Coresponds with create - File reader will retrieve data stored in SQL | Business Logic Layer | READ | Heatmap | Visual Studios | 3
C# will corepsond with SQL to read and create the heatmap
7 | User will be able to update the Earthquake by ID/ Update selection | Business Logic Layer | UPDATE | Heatmap | Visual Studios | 0
Private and public functions will be used so data can not be manipulated - tests in place. Earthquake year can be updated to show heatmap for a different year
8 | User can delete their selection of location markers, polyline selection, polygon selection and now heatmap selection | Business Logic Layer | DELETE | Heatmap | Visual Studios | 2
C# code so the user can click delete or clear. User can delete the heatmap selection
9 | User can create markers by selecting a desired year - and can now select the heatmap option | Presentation Layer | CREATE | Heatmap | ASPX, HTML | 10
Heatmap will be created for the selected year by the user.
10 | Data on that year clicked will appear | Presentation Layer | READ | Heatmap | ASPX, HTML | 3
All information on that year will appear - number of earthquakes etc.
11 | User can delete selection/clear selection - just the heatmap or all data | Presentation Layer | DELETE | Heatmap | ASPX, HTML | 0
Delete button/ Clear selection button
12 | User can update selection to create new heatmap for a different year | Presentation Layer | UPDATE | Heatmap | ASPX, HTML | 2
Update selection button
Summary | [5 empty] | 55
In sprint four, project Ursula will now show a heat map. The user can see a heat map for each year of Earthquake data. They will now have the option to add a heatmap, show polygons, create polylines while viewing the data on each earthquake. All code will be CRUD complete.