## Sheet1
Product Backlog
ID | TeamMate | I want to be able to | So that…… | Due Date | Sprint
1 | Everyone | Create a vision statement | We can portray what our project brings to the table | 2021-01-27 | Lab 1
2 | Sarah Price | Create a timesheet to track hours worked on project | To keep track of updates and team member tasks | 2021-01-27 | Lab 1
3 | Scrum Master | Fill out into the scrum must go before handing in every sprint | To keep track of who is scrum master and what to hand in | 2021-01-27 | Lab 1
4 | Bishwash | Create UML diagram/Release Plan | We can have ready to use code for sprint 1 | 2021-01-27 | Lab 1
5 | Sarah D | Create and update a Product backlog | We have a to do list for our project | 2021-01-27 | Lab 1
6 | Everyone | Compile everything to write a report/presentation | We can present our project to Clay/students | 2021-01-27 | Lab 1
7 |  | Create the DML and sp_database | Data can be grabbed from the cvs file | 2021-02-10 | 1
8 |  | Write the C# application for the SP_Ursula | SQL can communicate to see the data | 2021-02-10 | 1
9 | Bibhu | Write a DDL for SQL | We can create a database for earthquakes | 2021-02-10 | 1
10 |  | Create location object | To communicate with SQL and C# on a location | 2021-02-10 | 1
12 |  | CRUD- UPDATE by Id and DELETE | Make the data more personal to the user | 2021-02-10 | 1
13 |  | Create markers on google maps with HTML | Visual Data | 2021-02-10 | 1
14 |  | Store Data with SQL to create polylines | Connect the differences between data | 2021-03-03 | 2
15 |  | CRUD- UPDATE by Id and DELETE Polylines | User is able to start from the beginning without taking away markers | 2021-03-03 | 2
16 |  | Create Polylines on a google map through specific data | Type in more than just the earthquake ID | 2021-03-03 | 2
17 |  | UPDATE selection to create new polyline | Clear/Delete/Update button on goog;e maps | 2021-03-03 | 2
18 |  | Store Data with SQL to create polygons |  | 2021-03-24 | 3
19 |  | CRUD for polygons | More user friendly data to work with | 2021-03-24 | 3
20 |  | File reader Location object with C# | Read the updated code to see more/different data | 2021-03-24 | 3
21 |  | Selection of markers/polygons by all factors on the google map | Can see the depth of the daata choosen | 2021-03-24 | 3
22 |  | Create and store data for heat map in SQL | A google map will show the depth of the earthquake | 2021-04-14 | 4
23 |  | CRUD for heatmap | Delete/Update and Remove different parts of the heat map | 2021-04-14 | 4
24 |  | Write C# Code to create the heatmap on the google map | Visualize the data even better | 2021-04-14 | 4
25 |  | CRUD in heatmap layer | Personalize the data set | 2021-04-14 | 4
26 |  | Select earthquakes by any category | Easy to manipulate data | 2021-04-14 | 4
27
28 | Sarah | Update Backlog report as needed | We can keep track of progress and what we have left | 2021-04-14 | ALL